## Executive Summary
Solution Core AI Website Project — Product Owner Documentation
Project Name | Solution Core AI Business Website
Project URL | https://solutioncoreai-website.pari-soleimani.workers.dev
Start Date | 2026-03-03
Timeline | 8 Weeks
Methodology | Scrum / Agile Product Owner Approach
Product Goal | Launch a professional business website that communicates Solution Core AI services, builds trust, and helps convert visitors into leads.
MVP Scope | Homepage, navigation, product/service sections, industries, contact CTA, footer, social links, customer support chatbot.
Success Metrics | Clear value proposition, mobile-friendly experience, working chatbot, contact path, stakeholder approval, production launch.
Product Owner Summary
As Product Owner, I owned the product vision, MVP scope, backlog, priorities, acceptance criteria, stakeholder communication, sprint review, QA approval, and launch readiness. I translated business goals into user stories, guided UI/UX decisions, reviewed implementation quality, clarified requirements, tested the chatbot/customer journey, and documented the product delivery plan.

## Gantt Chart
High-Level Gantt Chart — Solution Core AI Website MVP
Phase / Workstream | Owner | Deliverable | Week 1 Mar 03–Mar 09 | Week 2 Mar 10–Mar 16 | Week 3 Mar 17–Mar 23 | Week 4 Mar 24–Mar 30 | Week 5 Mar 31–Apr 06 | Week 6 Apr 07–Apr 13 | Week 7 Apr 14–Apr 20 | Week 8 Apr 21–Apr 27
Discovery & Requirements | Product Owner / PM | Problem statement, business goals, MVP scope, success metrics | ●
Product Strategy + API Planning | Product Owner, Tech Lead | Product roadmap, backlog, API/chatbot future integration plan |  | ●
UI/UX Design + Content Architecture | Product Owner, UX/UI Designer | Site map, wireframe, visual direction, content structure |  |  | ●
Development Sprint 1 | Frontend Developer | Homepage foundation, navigation, hero, responsive layout |  |  |  | ●
Development Sprint 2 | Frontend Developer, Product Owner | Services, products, industries, contact, footer |  |  |  |  | ●
Chatbot Build + API Readiness | Frontend Developer, Product Owner | Customer support chatbot MVP | [5 empty] | ●
QA, Testing + Refinement | QA, Product Owner, Stakeholders | QA checklist, defect log, content review, mobile review | [6 empty] | ●
Stakeholder Review + Launch | Product Owner, Stakeholders | UAT approval, launch, retrospective, version 2 backlog | [7 empty] | ●
Key Milestones
ID | Milestone | Date
M1 | MVP Scope Approved | 2026-03-09
M2 | Design Direction Approved | 2026-03-23
M3 | Core Website Complete | 2026-04-06
M4 | Chatbot MVP Complete | 2026-04-13
M5 | Stakeholder UAT Approval | 2026-04-27

## Sprint Backlog
Sprint Backlog — Scrum Product Owner View
Week | Sprint / Phase | User Story / Task | Priority | Owner | Acceptance Criteria | Status | PO Activity
1 | Discovery | Define customer problem and MVP goals | High | Product Owner | Problem, target user, and success metric documented | Done | Interview stakeholder; define scope
1 | Discovery | Create initial product vision and measurable outcomes | High | Product Owner | Vision and launch goal approved | Done | Write vision; align with manager
2 | Strategy / API | Create product backlog and prioritize MVP vs future features | High | Product Owner | Backlog ranked by business value and effort | Done | Prioritize roadmap; define MVP
2 | Strategy / API | Document chatbot/API future needs | Medium | Tech Lead / PO | API readiness notes captured for future AI/CRM integration | Done | Clarify integration assumptions
3 | UI/UX | Design user journey and information architecture | High | UX / PO | Navigation and page sections are understandable | Done | Review wireframe; approve content flow
3 | UI/UX | Finalize brand direction, colors, and service content | High | UX / PO | Visual direction supports AI consulting brand | Done | Approve copy and style
4 | Development Sprint 1 | Build homepage foundation and hero section | High | Frontend Dev | Homepage loads, logo displays, navigation works | Done | Review demo; provide feedback
4 | Development Sprint 1 | Implement responsive layout framework | High | Frontend Dev | Desktop and mobile layout remain readable | Done | Validate responsive behavior
5 | Development Sprint 2 | Build services, products, industries, and contact sections | High | Frontend Dev | All content sections present with consistent styling | Done | Accept/reject content and layout
5 | Development Sprint 2 | Add footer and social links | Medium | Frontend Dev | Footer displays company info and social icons | Done | Review links and brand wording
6 | Chatbot | Create customer support chatbot UI | Medium | Frontend Dev | Button opens small support window and closes correctly | Done | Define greeting and quick replies
6 | Chatbot | Add chatbot keyword response logic | Medium | Frontend Dev / PO | Bot responds to AI, website, automation, contact questions | Done | Write support responses
7 | Testing / QA | Run QA checklist and fix defects | High | QA / PO | No blocking layout, navigation, or chatbot issues | Done | Log defects; approve fixes
7 | Testing / QA | Validate stakeholder feedback and final copy | High | PO / Stakeholder | Content is clear and professional | Done | Review with manager/stakeholder
8 | Launch | Publish production website | High | Frontend Dev / PO | Website deployed and accessible by URL | Done | Approve launch
8 | Launch | Create retrospective and Version 2 backlog | Medium | Product Owner | Post-launch improvements documented | Done | Capture lessons learned

## Scrum PO Duties
Scrum Product Owner Day-to-Day Duties
Scrum Event / Activity | Cadence | Product Owner Responsibility | Output | Business Value | Example for This Website
Daily Standup | Daily | Clarify priority, remove blockers, confirm progress | Updated blockers and decisions | Keeps delivery moving | Clarified chatbot behavior and content changes
Backlog Refinement | Weekly | Update user stories, acceptance criteria, and priority | Refined backlog | Builds the right work first | Prioritized homepage, service pages, contact CTA before advanced chatbot
Sprint Planning | Every sprint | Define sprint goal and commit to priority features | Sprint plan | Creates focused execution | Sprint 1: website foundation; Sprint 2: content sections
Sprint Review | End of sprint | Review demo against acceptance criteria | Accepted/rejected work | Ensures quality and stakeholder fit | Reviewed chatbot design and requested smaller support window
Stakeholder Review | Weekly/At milestones | Communicate status, tradeoffs, risks, and decisions | Decision log | Maintains alignment | Aligned final V1 launch with customer-facing goals
Retrospective | End of project | Capture what improved and next version opportunities | Lessons learned | Improves future delivery | Version 2: lead capture form, CRM, AI API integration

## QA & Risks
QA Checklist, Risks, and Launch Readiness
Category | Check Item | Owner | Priority | Expected Result | Status | Risk | Mitigation
Navigation | All menu links scroll to correct sections | QA / PO | High | No broken internal links | Done | Users cannot find services | Test all anchor links
Responsive | Website works on desktop and mobile | QA / PO | High | Layout remains readable | Done | Poor mobile experience | Test common screen sizes
Branding | Logo, colors, typography are consistent | PO / UX | Medium | Professional AI consulting image | Done | Weak credibility | Final visual review
Content | Service descriptions are clear and concise | PO | High | Visitor understands value quickly | Done | Confusing messaging | Review copy with stakeholder
Chatbot | Chatbot opens and closes correctly | QA / Dev | High | Small popup works on click | Done | Chat blocks page | Test open/close and z-index
Chatbot | Quick replies and keyword responses work | QA / PO | Medium | Bot answers common questions | Done | Weak user support | Test AI, website, automation, contact
Contact | Email CTA uses correct address | QA / PO | High | User can contact company | Done | Lead loss | Test mailto link
Launch | Production URL is accessible | Dev / PO | High | Website opens publicly | Done | Launch failure | Verify deployed URL